Field supervision report

- General Information

| Staff Name | Dr. Moe Hnin Phyu |
| --- | --- |
| Co-traveler(s) |  |
| Township(s) visited | Pyigyitagon |

- Detail information of field supervision

| Date | 31 October 2024 |
| --- | --- |
| Place(s) of visit | Visit to AMP + PGTG SDP |
| Program activities | Surprise check to AMP + PGTG SDP and two DRTB field officers. As the visit day is last day of the month, they are preparing MEAL reports of the month and met the respective FO. - 1 FO covers to PGTG and PyiOoLwin townships starting from November 2024 - PGTG: 9 ongoing patients in Pyigyitagon including 3 finished treatments in October and there is one potential RR patient in the waiting list. RR result was obtained on 7.10.2024 and patient was going to UMTBC for pre-enrolled assessment. On visit day, UMTBC’s medico-social worker contact to PGTG FO for the new DRTB patient and shared patient’s contact address but can’t call to patient as his number is out of service. 1st time clinical visit was conducted with rental car (120,000MMK per trip from 9 AM to 4 PM) but second time was by FO’s motorcycle & not reported to MEAL team. PFA was currently performed to patients in PGTG and will be rolled out POL in coming month. SDP running cost was managed by PICTS team. - PowerStation for each project was provided and 1 is used for printing and another 1 is used for continuous power supply to Wifi. There are 2 printers, one was not supported by the output from PowerStation. - Patient Zin Thu, 33yr, RR result on 23.7.2024, a case of RVI with MDRTB who died before treatment started but no household contact information and CI performance - POL: 13 ongoing patients, 3 are from enclosed setting and 10 are from community and clinical visit was conducted by office cars - Checking SE record book: there was no space for recording regimen changes, not filling eligible month for pre-enrolled support and submitted to MEAL team without any feedback on that Project issues - Combine supervision visit record for AMP & PGTG - Two potential DRTB patients but one case can identify and contact - PowerStation output cannot support PANTUM printer - Treatment delayed patients were found especially before June 2024 - 2nd time clinical visit record was not included in the narrative report and reported to MEAL team - Contacts of pt Zin Thu were not encountered contact investigation - Missing data in SE record but not received feedback from MEAL team |
| M&E activities | Random checking of DRTB SE record and missing data was found. |

- Recommendations

| Recommendation | - To have separate supervision visit record (one book/township) - To communicate with UMTBC focal for RR result - To recruit volunteers for potential patients - To change high output PowerStation with the existing one - To find out the reason for treatment delay during home visit - To include 2nd clinical visit report in FO narrative and M&E report together with reason for visit - To contact Zin Thu’s household members for screening - PM and DPD to follow up with MEAL team for missing data in SE record but not received feedback |
| --- | --- |

Submitted by

Name:	Dr. Moe Hnin Phyu

Designation: Deputy Program Director (DRTB)

Date:	12.11.2024