Field supervision report

- General Information

| Staff Name | Dr. Moe Hnin Phyu |
| --- | --- |
| Co-traveler(s) | Dr. Ko Ko Htwe, Dr. Aung Naing Soe, Dr. Wai Yan Kyaw |
| Township(s) visited | Meikhtila |

- Detail information of field supervision

| Date | 23.4.24 – 25.4.24 |
| --- | --- |
| Place(s) of visit | Meikhtila SDP, Patient home visit |
| Program activities | Meikhtila (March 2024) Total enrolled patient supported – 27 (Meikhtila –18, Wundwin –4, Tharsi -4, Mahlaing–1) No of patients receive through ATM –16, Cash –11, wave –0 No of DOT received patients –15 (Meikhtila –12, Wundwin –2, Tharsi -0, Mahlaing–1) No of DOT providers – 13 (Meikhtila –10, Wundwin –0, Tharsi -2, Mahlaing–1) No of XDR/ Pre-XDR patients - 4 No of patients on single dose (OSSTR) – 0 No of patients on Single dose (OLTR) – 17 No of patients on BPaL regimen – 5 (Meikhtila –3, Wundwin –1, Tharsi -1, Mahlaing–0) No of patients specialized regime - 1 DOT coverage for MHL (CAT A township) is 67%. (Among 18 DRTB patients at CAT A Meikhtila, 12 DRTB patients received DOT service from 10 DOT vol) TB diagnostic service availability at Meikhtila TBC. Sputum Microscopy and GXP ultra – available at the office days. Base line and follow up investigation services available at quotation lab in (Yadanar Laboratory) Meikhtila during follow up visit. CXR – outsourcing at Htun Private Specialist Clinic (17000MMK per digital slide with opinion). NTP HR at Meikhtila TBC - Team Leader – 1, TB coordinator – 1, PHSI – 1, Lab tech – 1, worker – 1 2 follow up days per month for DRTB patients at Meikhtila TBC. Drugs were already dispensed to outside townships TBC and DRTB patients after following up show at MHL TBC can withdraw drug supply from respective outside township TBC. Union HR at Meikhtila SDP - FO – 2 (1 was assigned to MHL TBC to help the patients care and support, Peer Counselor – 1, Office volunteer– 1) - When seconded DA is assigned, NTP attached FO will plan to delegate and assign some NTP workload like NTP quarterly report, culture result, DRTB register, open MRS, etc) SDP Rental fee – 3 Lakh per month from January to June 2024. Currently, there is shortage in running water supply. List of no DOT volunteer in Jan and February 2024 - Yan Lin Naing, 30 yrs, DRTB no. 22/22, OLTR, from Shan Nge group, Ye Ngan, MHL, Outcome date 22.2.2024 (reason for No DOT: patient live in POL although he was registered in MHL) - U Zaw Win, 43yr, DRTB no. 27/22, OLTR, from Ingyin Su village, Nyaungpinshae group, MHL, Outcome date 31.3.2024 (reason for No DOT: Can’t recruit volunteer in his village and patient live alone in his home) - Min Thu Maung, 34 yrs, DRTB no. 1/23, OLTR, from military hospital MHL (Reason for no DOT: military hospital has their own DOT and volunteer can’t enter to military hospital daily) - Ko Myo Thant, 38 yrs, DRTB no. 4/23, OLTR, No DOT volunteer in Jan but had in Feb 2024 - Wunna Aung, 38 yrs, DRTB no. 7/23, OLTR, from military hospital MHL (Reason for no DOT: military hospital has their own DOT and volunteer can’t enter to military hospital daily) - Thandar Oo, 23 yrs, DRTB no. 9/23, OLTR, from Sipinthar village, MHL (Reason for no DOT: She live in her aunt house and refuse DOT) - Htun Hla Aung, 35 yrs, DRTB no. 13/23, Mono resistant, Magyichauk, MHL (Reason for No DOT: FO think volunteer can’t assign in mono resistant case) - Sandar Khaing, 36 yrs, DRTB no. 32/22, OLTR, (Reason for no DOT: there was volunteer gap while previous volunteer drops out and finding new volunteer) - Aung Khaing, 31 yrs, DRTB no. 26/22, OLTR, from military hospital MHL (Reason for no DOT: military hospital has their own DOT and volunteer can’t enter to military hospital daily) Home visit to DRTB patient Ko Min Min Han, 31 yrs, DRTB no. 15/23, on Month 9 of individualized pre-XDR treatment. He lives in Yae Sone, Wundwin and had DOT volunteer. During the visit, the patient's general condition was fine with no major side effects except tingling and numbness of lower limb and bronze color skin. Previously he was hospitalized 3 times during DRTB treatment with the diagnosis of Anaemia and blood transfusion ~ 6 bot was undergone. Therefore, hospitalization support and specialist consultation support were provided. Moreover, nutritional support is provided as his current body weight is 36.8 kg and no dramatic increase in body weight compared with initial body weight 34 kg. He had a previous history of taking DSTB treatment in 2022. (? For miliary TB and no GXP was tested at that time). 2 months after miliary TB treatment, he suffered hemoptysis again and consulted at MHL TBC and diagnosed as pre-XDR TB. He got monthly socio-economic support with ATM (KBZ bank). While interviewing the patient, he found out about his disease, treatment duration and mode of transmission. He said that field officers usually visit his home on a bimonthly basis. He had 3 household members, and they all underwent CXR screening for contact tracing. Home visit to Daw Mar Mar Wai, 49 years, DRTB no. 3/23, OLTR treatment started on 24.1.2023. She has tingling and numbness but no other major side effect. She got monthly support with ATM. During home visit, her Blood pressure was 100/70 mmHg, PR 80/min, SPO2 -96% and general condition is fair. She has DOT volunteer, Ma Si Si who has been trained for DRTB 3 times. DOT volunteer lives 20 minutes motorcycle drive away from patient home and she tried to provide in person DOT at least 3 times/week and other days with phone DOT. During home visit, the patient has no surgical mask in hand and instead she was using FFP2 respirator. DOT volunteer carried no DOT book and project documents during visit. Home visit to Daw Than Kywal, 74 yrs, DRTB no. 10/23, OLTR started on 16.3.2023, currently on month 12 of treatment. She is lying on the bed and had slight dyspnoea after taking a bath. She had history of hospitalization for anaemia and blood transfusion 4 bot was completed. During home visit, vital signs are stable and no other side effect except dyspnoea on exertion. Encourage to take nutritious food as she does not want to eat red meat. She got monthly support via ATM. DOT volunteer is her daughter and got on job training but no comprehensive training. Home visit to Ma Tint Tint Tun, 30 yrs, who is on 1 month of BPaL regimen. Currently she has no major side effect. An extended family who lives in one compound and has 6 household contacts, two of them encountered CXR screening and the result is good. Others are appointed for CXR screening on 26th April 2024. She had DOT volunteer who is peer counsellor of MHL SDP, and regular DOT and counselling was done via phone. Finding; Instruction for action taken. There was remaining two issues to address from previous visit recommendation.; To address within one month.. Incomplete data and title in DRTB mapping; To update the title and add 2024 DRTB cases. Volunteer has not been trained in comprehensive training; Encourage volunteer to join the training. DOT coverage was ~ 53% in the first two months of 2024.; Except patients from military hospital, to recruit and assign DOT volunteer as fast as possible and fill in the remark column if no DOT volunteer.. Stock balance, report and ground check was match.; Keep the good practice.. Finance cover copy for October and December 23 is missing.; To print out hard copies of finance cover sheet (Oct and Dec) for recording documents.. Cash book record kept only in soft copy (23 and 24) and cash book is only updated when finance report is finalized.; To print out cash book hard copies starting from January 2024 and FO needs to update daily expense in cash book format.. During home visit, the patient has no surgical mask in hand and instead she was using FFP2 respirator.; FO must know standardization of stock items and distribute IEC and promo items to eligible DRTB patients.. No easy check reference (hard copies) in SDP (TA scheme 2024, standardized utilization of stock items, etc).; To print out these documents for easy check reference.. |
| M&E activities | Presumptive register - Tsh S/N 14/24 referred from community > to note COPD instead of COPT under CXR result - Ma Aye Aye Khaing, 2yr follow up patient > to tick past history of TB under risk factor column - Ma Aye Aye Hlaing case found at DRTB contact > to fill index case registration no - U Thar Hlaing, 2yr follow up patient > to tick past history of TB under risk factor column - U Chan Hmwe close contact of 10/23, CXR opinion – active infective changes in LUZ but no GXP was done due to cartridge shortage starting from 20.3.24 to 10.4.24. SE record - For patients with no DOT vol > to note down reason for no DOT under remark session in SE record - Ma Tint Tint Tun R/N-7/24 > to fill DRTB regimen (BPalM). SPS register U Thiha Lin (5/24), Ma Tint Tint Htun (7/24), Daw Moe Moe Lwin (4/24), Ko Min Thu Maung (6/24), U Aung Zaw Lin (3/24), Ko Chan Aye (1/24)> To tick “No” if there is no reimbursement is provided during reporting period. Ko Chan Aye (1/24)> to tick P8 while recording body weight 16.6 accessing the patient is eligible for nutrition support at the same month. Ma Tint Tint Htun (7/24), P8 30000MMK was supported for current month and reimbursement 30000MMK for previous month but recorded 60000MMK for current month. |

- Recommendations

| Recommendation | - FO to encourage volunteers to join annual comprehensive training. - FO to improve DOT coverage. - FO to encourage every eligible DRTB patient to receive AIS SPS support. - FO to strengthen DOT application usage for the patients who live far away from Meiktila and registered in MHL township. - FO to update monthly Nutrition and TA record kept in patient. - FO to remind all DOT volunteers to carry DOT books and project documents during DOT activities and supervision visits. - FO to keep in touch with project updates and need to check update email. |
| --- | --- |

Submitted by

Name:	Dr. Moe Hnin Phyu

Designation: Deputy Program Director

Date:	26.4.2024