Field supervision report

- General Information

| Staff Name | Dr. Thant Nay Aung |
| --- | --- |
| Co-traveler(s) |  |
| Township(s) visited | PTG |

- Detail information of field supervision

| Date | 9.9.2024 |
| --- | --- |
| Place(s) of visit | SDP, Patient’s Residence |
| Coordination |  |
| Program activities | - Checked the program documents |
| M&E activities | Cannot be done at the visit |

- Actions Needs to be Done

| No | Issues | Recommendations | Timeline | Responsible Entity |
| --- | --- | --- | --- | --- |
| 1 | Assigned space for DRTB team at AMTZ+PTG SDP is inconvenient to work under very hot conditions and space limitation | To move to a new SDP convenient to work for both teams | Dec | PM, FO |
| 2 | DRTB patients with underlying DM needs more attention and HE | To provide frequent monitoring of TB-DM patients by PC, FO and Medical Officer and PC should provide the DM related information printed and lists of food items suitable for DM | Regularly | PC, FO and MO |
| 3 | Found Bdq is missing in the provided drugs from township for Daw Lone (37/24) and volunteer and FO are not aware of that | To check the drugs issued by township NTP to DRTB patients and to supervise the volunteers whether they do provide DOT checking the right drug, right dosage | Regularly | FO |
| 4 |  |  |  |  |
| 5 |  |  |  |  |

Submitted by

Name:	Dr. Thant Nay Aung

Designation: Program Manager (CBDRTBC)

Date:	9.9.2024