Field supervision report

- General Information

| Staff Name | Dr. Thant Nay Aung |
| --- | --- |
| Co-traveler(s) |  |
| Township(s) visited | Pakokku |

- Detail information of field supervision

| Date | 19.11.2024 |
| --- | --- |
| Place(s) of visit | PKU SDP and patients’ home |
| Coordination |  |
| Program activities | - Joined volunteer training at NYO in the evening October Data for PKU Sr No; Indicators; Total; Remark. 1; No: of DR-TB patients nominated for pre-enrolled support; 0. 2; No: of newly pre-enrolled DR-TB patients supported; 0. 3; No: of total pre-enrolled DR-TB patients supported (new+old); 0. 4; No: of DR-TB patients nominated for enrolled support; 15. 5; No: of newly enrolled DR-TB patients supported; 0. 6; No: of total enrolled DR-TB patients supported (new+old); 13. 7; No: of patients received through ATM; 5. 8; No: of patients received through Wave; 0. 9; No: of patients received through Cash; 10. 10; No: of BPaLM/BPaL patients; 6. 11; No: of OSSTR patients; 0. 12; No: of OLTR patients; 7. 13; No: of Pre XDR patients; 2. 14; No: of IR patients; 0. 15; No: of volunteer attendee in training conducted during this month; 0. 16; No: of reported volunteers; 8. 17; No: of volunteers who provide DOT; 8. 18; No: of DR-TB patients who receive DOT; 10. Visit to DRTB patient (8/24, 9/24) |
| M&E activities | Cannot be done at the visit |

- Actions Needs to be Done

| No | Issues | Recommendations | Timeline | Responsible Entity |
| --- | --- | --- | --- | --- |
| 1 | Found DRTB patients not taking the prescribed ancillary drugs properly (ORS preparation with less water and mistaking of ancillary drugs) To communicate and asse | To supervise the treatment for comorbid diseases and side effects by FO and volunteers | regularly | FO |
| 2 | CI and contact referral process by volunteer not planned according to schedule. Form 12 referral date is not actual referred date. | To conduct the contact referral and CI according to schedule and record the actual referral date | regularly | FO |
| 3 | Only Phone DOT for DRTB patient from Gangaw | Virtual DOT to monitor and if patient cannot communicate well, to stop DOT |  | FO |
| 4 | Physician from PKU- not interested in DRTB follow up care | To coordinate with TB focal and MO for complicated cases to refer to Magway or PKU physician | regularly | FO |

Submitted by

Name:	Dr. Thant Nay Aung

Designation: Program Manager (CBDRTBC)

Date:	29.11.2024